## Sheet1
Responsibility Assignment Matrix
Project Name: Internet Banking System
|  |  | Author | Version | Date | Comment
|  |  | Salsabeel | 1 | 27/4/2019 | Assign roles of planning phase
|  |  | Salsabeel | 1.1 | 27/4/2019 | Add Introduction Section
|  |  | Salsabeel | 2 | 2019-02-05 | Update Roles
|  |  | Salsabeel | 3 | 2019-09-05 | Add roles for design tasks
Introduction: A responsibility assignment Matrix (RAM), also known as RACI matrix, describes the participation by various roles in completing tasks or deliverables for a project or business process. It is used for clarifying and defining roles and responsibilities in cross-functional or departmental projects and processes. It defines four roles: R = Responsible (also Recommender) A = Accountable (also Approver or final approving authority) C = Consulted (sometimes Consultant or counsel) I = Informed (also Informee)
|  | Task / Responsible | Ahmed | Alaa | Hassan | Khadija | Salsabeel | Sondos
|  | Configuration management tool |  | A | I |  | R
|  | Risk Sheet |  |  | R | I
|  | Issues Sheet |  |  | R | I
|  | Software Requirements Specification (SRS) |  | R |  | I
|  | SRS Peer Review Sheet |  |  | C |  | R | I
|  | Requiremets Traceablity matrix (RTM) | I |  |  |  | A | R
|  | SIQ |  |  |  | R |  | I
|  | Project Plan Document | R | C | I |  | A
|  | Project Schedule |  |  |  |  | I | R
Design phase tasks
|  | Update project plan |  |  | R |  | I
|  | GUI design |  |  |  | R | I
|  | High level design |  |  |  | I | R
|  | Desgin Data Models | R |  |  |  |  | I
|  | Design class diagram |  | R | I
|  | Write design document |  | R |  |  | A
|  | Write design document peer review sheet | R |  | A
|  | update RTM |  | A |  | I |  | R
|  | Update RACI matrix |  |  |  |  | R