## SRS-PR Sheet
Design document Peer Review Sheet
| Version | Author | Date | Comment
| 1 | Ahmed | 2019-09-05 | Initiate design document peer review
| 2 | Ahmed | 2019-10-05 | Update peer review sheet
Design type | Issue ID | Design document reference Index | Issue Description | SRS ID | Priority | Comments | Review by | Review Date
High level design | Bank_Sys_Design_HLD_Issue_001 | Bank_SYS_HLD_client_005 Bank_SYS_HLD_admin_005 | missing in( C)(2) to check balance before transferring money to an account in the same bank | BANK_SYS_SRS_TR_R008 | High | after adding check balance request , we need to to elaborate response in two cases 1- customer balance covers transaction& doesn't exceed the amount he can transfer to aspecific account. 2- customer balance is greater than transaction ot exceeds the amount he can transfer to aspecific account. | Khadija | 2019-10-05
| Bank_Sys_Design_HLD_Issue_002 | missing | missing that the admin can make request to view an account balance . | BANK_SYS_SRS_Admin_R007 | High
| Bank_Sys_Design_HLD_Issue_003 | missing | missing that the admin can make request to view the account previous transactions. | BANK_SYS_SRS_Admin_R007 | High
| Bank_Sys_Design_HLD_Issue_004 | Bank_SYS_HLD_client_006 Bank_SYS_HLD_admin_006 | missing to elaborate the response in case customer wants to transfer amount of money greater than his balance to other bank or exceeds the amount he can transfer to a specific account after (D)(3) | BANK_SYS_SRS_TR_R008 BANK_SYS_SRS_TR_R027 | High
Detailed Design | Bank_Sys_Design_DD_Issue_001 | Detailed Design Class Diagram Document Version 1.1 | Missing relation between transaction and previous transaction ,it should be a composition as we discussed |  | High |  | Hassan | 2019-10-05
| Bank_Sys_Design_DD_Issue_002 | Detailed Design Class Diagram Document Version 1.1 | Unclear Relation between "Previous Transaction" and Account , it should be between "Transactions " and "Previous Transactions" |  | High
| Bank_Sys_Design_DD_Issue_003 | Detailed Design Class Diagram Document Version 1.1 | Relationship between "Account" and "Transactions" is one to one , it should be one to many based on the same logic we used in ERD. |  | Medium | The Relationship between can be 1 to 1 based on the emplementaion of the syatem but in this case we would have conflict between ERD document and Class Diagram Document
| Bank_Sys_Design_DD_Issue_004 | Detailed Design Class Diagram Document Version 1.1 | Unclear Relation between " Admin" and "Client" |  | Medium | <<use>> between admin and Client is unclear we may assume it's something like the relation between Bank and Client like in this link https://creately.com/diagram/example/ihww1rk21/online%20banking%20system
Data Model | Bank_Sys_Design_DM_Issue_001 | Bank_Sys_DM_ADMIN_001 | 1-when admin login or register sucessfully he will be redirected to admin home page not customer page 2-verifecation code is sent in case of register not login 3- to logi he need to enter user name ,password and national ID | BANK_SYS_SIQ_Q29 BANK_SYS_SIQ_Q30 | High |  | Sondos | 2019-10-05
| Bank_Sys_Design_DM_Issue_002 | Bank_Sys_DM_ADMIN_002 | 1-verifecation code is sent in case of register | BANK_SYS_SIQ_Q29 BANK_SYS_SIQ_Q30 | Medium
| Bank_Sys_Design_DM_Issue_003 | Missing | Admin can also add user not just remove | BANK_SYS_SIQ_Q10 BANK_SYS_SIQ_Q31 BANK_SYS_SIQ_Q32 | High
| Bank_Sys_Design_DM_Issue_004 | Bank_Sys_DM_ADMIN_004 | No SRS or CRS Related to this piece of design |  | High
| Bank_Sys_Design_DM_Issue_005 | Bank_Sys_DM_ADMIN_005 | Admin will be redirectec to Admin Home Page not customer home page | BANK_SYS_SIQ_Q31 | High
| Bank_Sys_Design_DM_Issue_006 | Bank_Sys_DM_ADMIN_006 | Admin will be redirectec to Admin Home Page not customer home page | BANK_SYS_SIQ_Q31 | High
| Bank_Sys_Design_DM_Issue_007 | Bank_Sys_DM_ADMIN_008 | the previous transaction page will not all the transactions directly . Transactions will be shown based on which he will choosse from the drop down menu 10,20,30 transactio | BANK_SYS_SIQ_Q22 | Low
| Bank_Sys_Design_DM_Issue_008 | Missing | request to the user data base to ensure that befor transfere mony the user balance is begger than the transferred money | BANK_SYS_SIQ_Q43 | High
| Bank_Sys_Design_DM_Issue_009 | Missing | What if the user wants to transfer money to account with the our bank? | BANK_SYS_SIQ_Q4 BANK_SYS_SIQ_Q41 | High
| Bank_Sys_Design_DM_Issue_010 | Bank_Sys_DM_CST_001 | the verification code is in case of registeration only | BANK_SYS_SIQ_Q29 BANK_SYS_SIQ_Q30 | High
| Bank_Sys_Design_DM_Issue_011 | Bank_Sys_DM_CST_002 | the verification code is in case of registeration only | BANK_SYS_SIQ_Q29 BANK_SYS_SIQ_Q30 | Medium
| Bank_Sys_Design_DM_Issue_012 | Bank_Sys_DM_CST_003 | No SRS or CRS Related to this piece of design |  | High
GUI | Bank_Sys_Design_GUI_Issue_001 | Bank_SYS_DSN_001, Bank_SYS_DSN_002, Bank_SYS_DSN_003, Bank_SYS_DSN_010, Bank_SYS_DSN_011, Bank_SYS_DSN_012, Bank_SYS_DSN_013, Bank_SYS_DSN_015 | fields constrains must be written beside the fields in the wireframe |  | High |  | Salsabeel | 2019-10-05
| Bank_Sys_Design_GUI_Issue_002 | missing | missing screen when user enters wrong verification code | BANK_SYS_SRS_Reg_R026 | High
| Bank_Sys_Design_GUI_Issue_003 | Bank_SYS_DSN_015 | Admin page wireframe should contain Admin user name not customer user name |  | High
| Bank_Sys_Design_GUI_Issue_004 | missing | missing screen of previous transactions error message when user doesn't have transactions in the requested period | BANK_SYS_SRS_PT_R015 | High
| Bank_Sys_Design_GUI_Issue_005 | Bank_SYS_DSN_011 | wrong error message when user exceeds the amount. It should be "You have exceeded the amount of money allowed to be transferred" | BANK_SYS_SRS_TR_R027 | High
| Bank_Sys_Design_GUI_Issue_006 | Bank_SYS_DSN_012 | wrong message text when user enters wrong account id. It should be "You have entered an invalid account , Please try again" | BANK_SYS_SRS_TR_R007 | Medium
| Bank_Sys_Design_GUI_Issue_007 | Bank_SYS_DSN_013 | wrong message text when user enters amount greater than his balance. It should be "you don't have the required amount , please check your balance" | BANK_SYS_SRS_TR_R008 | Medium
| Bank_Sys_Design_GUI_Issue_008 | Bank_SYS_DSN_014 | unclear coloring of amount in listing page, should be explained by modifying "from account id" and "to account id" | BANK_SYS_SRS_PT_R021, BANK_SYS_SRS_PT_R022 | High