## SRS-PR Sheet
Design document Peer Review Sheet
| Version | Author | Date | Comment
| 1 | Ahmed | 2019-09-05 | Initiate design document peer review
| 2 | Ahmed | 2019-10-05 | Update peer review sheet
Design type | Issue ID | Design document reference Index | Issue Description | SRS ID | Priority | Comments | Review by | Review Date
High level design | 1- | Bank_SYS_HLD_client_005 Bank_SYS_HLD_admin_005 | missing in( C)(2) to check balance before transferring money to an account in the same bank | BANK_SYS_SRS_TR_R008 | High | after adding check balance request , we need to to elaborate response in two cases 1- customer balance covers transaction& doesn't exceed the amount he can transfer to aspecific account. 2- customer balance is greater than transaction ot exceeds the amount he can transfer to aspecific account. | Khadija | 2019-10-05
| 2- | missing | missing that the admin can make request to view an account balance . | BANK_SYS_SRS_Admin_R007 | High
| 3- | missing | missing that the admin can make request to view the account previous transactions. | BANK_SYS_SRS_Admin_R007 | High
| 4- | Bank_SYS_HLD_client_006 Bank_SYS_HLD_admin_006 | missing to elaborate the response in case customer wants to transfer amount of money greater than his balance to other bank or exceeds the amount he can transfer to a specific account after (D)(3) | BANK_SYS_SRS_TR_R008 BANK_SYS_SRS_TR_R027 | High
Detailed Design | [6 empty] | Hassan
Data Flow Diagram |  | Bank_Sys_DM_ADMIN_001 | 1-when admin login or register sucessfully he will be redirected to admin home page not customer page 2-verifecation code is sent in case of register not login 3- to logi he need to enter user name ,password and national ID | BANK_SYS_SIQ_Q29 BANK_SYS_SIQ_Q30 | High |  | Sondos | 2019-10-05
|  | Bank_Sys_DM_ADMIN_002 | 1-verifecation code is sent in case of register | BANK_SYS_SIQ_Q29 BANK_SYS_SIQ_Q30 | Medium
|  | Missing | Admin can also add user not just remove | BANK_SYS_SIQ_Q10 BANK_SYS_SIQ_Q31 BANK_SYS_SIQ_Q32 | High
|  | Bank_Sys_DM_ADMIN_004 | No SRS or CRS Related to this piece of design |  | High
|  | Bank_Sys_DM_ADMIN_005 | Admin will be redirectec to Admin Home Page not customer home page | BANK_SYS_SIQ_Q31 | High
|  | Bank_Sys_DM_ADMIN_006 | Admin will be redirectec to Admin Home Page not customer home page | BANK_SYS_SIQ_Q31 | High
|  | Bank_Sys_DM_ADMIN_008 | the previous transaction page will not all the transactions directly . Transactions will be shown based on which he will choosse from the drop down menu 10,20,30 transactio | BANK_SYS_SIQ_Q22 | Low
|  | Missing | request to the user data base to ensure that befor transfere mony the user balance is begger than the transferred money | BANK_SYS_SIQ_Q43 | High
|  | Missing | What if the user wants to transfer money to account with the our bank? | BANK_SYS_SIQ_Q4 BANK_SYS_SIQ_Q41 | High
|  | Bank_Sys_DM_CST_001 | the verification code is in case of registeration only | BANK_SYS_SIQ_Q29 BANK_SYS_SIQ_Q30 | High
|  | Bank_Sys_DM_CST_002 | the verification code is in case of registeration only | BANK_SYS_SIQ_Q29 BANK_SYS_SIQ_Q30 | Medium
|  | Bank_Sys_DM_CST_003 | No SRS or CRS Related to this piece of design |  | High
Data Model ERD | [6 empty] | Sondos
GUI | [6 empty] | Salsabeel